ENHANCED ETL

MIGRATION PLAN v2.0

CyberArk PAS → Delinea Secret Server

Risk-Aware | Bottleneck-Mitigated | Enterprise-Scale

Addressing: NHI Complexity | Integration Rework | Scalability | Compliance

Prepared by: Jeremy Smith, CISSP

January 2026

# Executive Summary: Why v2.0?

This enhanced ETL plan incorporates lessons learned from enterprise PAM migrations and addresses five critical bottlenecks identified in pre-migration analysis:

| Bottleneck | Risk Level | v2.0 Mitigation |
| --- | --- | --- |
| Non-Human Identities (NHIs) | CRITICAL | Dedicated NHI discovery and staged migration |
| Integration Rework | HIGH | Integration dependency mapping and cutover planning |
| Permission Granularity Loss | HIGH | Permission translation matrix with stakeholder approval |
| Scalability at 20K+ Accounts | MEDIUM | Batched migration with performance benchmarking |
| Compliance/Audit Trail | HIGH | Pre/post compliance validation and audit reconciliation |

## Key Changes from v1.0

• NEW: Dedicated NHI (Non-Human Identity) discovery and migration track

• NEW: Integration dependency mapping before any migration

• NEW: CCP/AAM application credential cutover planning

• NEW: Permission translation matrix with stakeholder sign-off

• NEW: Scalability benchmarking before production load

• NEW: Iris AI configuration for post-migration anomaly detection

• NEW: Compliance checkpoint gates at each phase

• ENHANCED: Parallel running extended to 4-6 weeks (was 2-4)

• ENHANCED: Rollback triggers with specific thresholds

# Migration Risk Register

All identified risks with probability, impact, and mitigation strategies.

| Risk ID | Risk Description | Prob | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | NHI credentials break applications | High | Critical | Staged NHI migration with app team coordination |
| R2 | CCP/AAM integrations fail at cutover | High | Critical | Parallel API availability, phased cutover |
| R3 | Permission loss causes access issues | Medium | High | Translation matrix, UAT before cutover |
| R4 | SIEM integration gap during migration | Medium | High | Dual logging during parallel period |
| R5 | Scalability issues at full load | Medium | Medium | Benchmark at 50%, 75%, 100% load |
| R6 | Audit trail gaps for compliance | Medium | High | Export all CyberArk logs before cutover |
| R7 | PSM recordings not accessible | Low | Medium | Archive to separate storage pre-cutover |
| R8 | Team unfamiliar with Secret Server | Medium | Medium | Training in parallel period |

PHASE 1: ENHANCED DISCOVERY & RISK ASSESSMENT

Duration: 3-4 Weeks  |  Focus: EXTRACT + ANALYZE

## 1.1 Standard Account Extraction

Extract all human identity accounts as in v1.0:

# Standard extraction

$safes = Get-PASSafe

$accounts = Get-PASAccount

$members = Get-PASSafeMember (for each safe)

$platforms = Get-PASPlatform

## 1.2 NEW: Non-Human Identity (NHI) Discovery

🔴 RISK: NHIs are the #1 cause of migration failures. Service accounts, API keys, and application credentials often have undocumented dependencies.

NHIs include:

• Service accounts (Windows services, scheduled tasks)

• Application credentials (retrieved via CCP/AAM)

• API keys and secrets

• Database connection strings

• DevOps pipeline credentials

• Machine identities (certificates, SSH keys)

# ENHANCED: Identify NHIs by usage pattern

$allAccounts = Get-PASAccount

# Flag accounts retrieved programmatically (likely NHI)

$nhiCandidates = @()

foreach ($account in $allAccounts) {

$activity = Get-PASAccountActivity -AccountID $account.id -Limit 100

# Check for programmatic access patterns

$appAccess = $activity | Where-Object {

$_.Action -eq 'Retrieve Password' -and

($_.PerformedBy -like '*AppUser*' -or

$_.PerformedBy -like '*CCP*' -or

$_.PerformedBy -like '*AAM*' -or

$_.ClientApp -ne 'PVWA')

}

if ($appAccess.Count -gt 0) {

$nhiCandidates += [PSCustomObject]@{

AccountId = $account.id

AccountName = $account.name

SafeName = $account.safeName

Platform = $account.platformId

AccessCount = $appAccess.Count

LastAppAccess = ($appAccess | Sort-Object Date -Descending)[0].Date

AccessedBy = ($appAccess.PerformedBy | Select-Object -Unique) -join ','

RiskLevel = 'HIGH - Application Dependency'

}

}

}

$nhiCandidates | Export-Csv "$extractPath\NHI_Candidates.csv" -NoTypeInformation

Write-Host "Identified $($nhiCandidates.Count) potential NHIs" -ForegroundColor Yellow

⚠️ CRITICAL: Each NHI requires application owner identification and cutover coordination.

## 1.3 NEW: Integration Dependency Mapping

🔴 RISK: Integrations are the #2 cause of migration failures. Every system that talks to CyberArk must be re-pointed.

Create integration inventory:

| Integration Type | Discovery Method | Cutover Complexity |
| --- | --- | --- |
| SIEM (syslog) | Check CyberArk syslog config | Low - reconfigure receiver |
| Ticketing (ServiceNow) | Check ITSM integration settings | Medium - API changes |
| CCP/AAM Applications | Audit CCP/AAM usage logs | HIGH - App code changes |
| PSM Connection Components | List PSM configurations | Medium - recreate in SS |
| AD/LDAP Sync | Check directory integration | Low - reconfigure |
| MFA (Duo, RSA) | Check authentication settings | Medium - RADIUS/SAML |
| SOAR Playbooks | Audit security automation | HIGH - API changes |

# Document all integrations

$integrations = @()

# Check syslog configuration

# (Manual: PVWA > Administration > Options > Syslog)

$integrations += [PSCustomObject]@{

Type = 'SIEM'

Target = 'siem.company.com:514'

Protocol = 'Syslog/CEF'

CutoverAction = 'Reconfigure Secret Server syslog to same target'

Owner = 'SOC Team'

Risk = 'Low'

}

# Check CCP/AAM applications

# Query Vault audit for CCP access

$ccpApps = Get-PASComponentDetail -Component CCP

foreach ($app in $ccpApps) {

$integrations += [PSCustomObject]@{

Type = 'CCP/AAM'

Target = $app.AppID

Protocol = 'REST API'

CutoverAction = 'Update app to Secret Server SDK/API'

Owner = 'TBD - App Team'

Risk = 'HIGH'

}

}

$integrations | Export-Csv "$extractPath\Integration_Dependencies.csv" -NoTypeInformation

## 1.4 NEW: Permission Translation Matrix

🔴 RISK: CyberArk has ~15 granular permissions. Secret Server has 4 roles. Translation requires stakeholder approval.

| CyberArk Permission(s) | Secret Server Role | What's Lost |
| --- | --- | --- |
| ManageSafe + ManageSafeMembers + BackupSafe | Owner | Nothing |
| AddAccounts + UpdateAccountContent + DeleteAccounts | Edit | Granular add/delete separation |
| RetrieveAccounts + UseAccounts | View | Distinction between view/connect |
| ListAccounts only | List | Nothing |
| InitiateCPMOperations only | View + RPC trigger | Requires custom role |
| SpecifyNextAccountContent | Edit | Specific permission lost |
| ViewAuditLog + ViewSafeMembers | List + Audit role | May need separate assignment |

⚠️ REQUIRED: Get stakeholder sign-off on permission translation before Phase 3.

# Generate permission translation report

$permissionReport = @()

$safeMembers = Import-Csv "$extractPath\SafeMembers.csv"

foreach ($member in $safeMembers) {

# Determine target role

$targetRole = 'List'  # Default minimum

$lostPermissions = @()

if ($member.ManageSafe -eq 'True' -and $member.ManageSafeMembers -eq 'True') {

$targetRole = 'Owner'

}

elseif ($member.AddAccounts -eq 'True' -or $member.UpdateAccountContent -eq 'True') {

$targetRole = 'Edit'

if ($member.AddAccounts -eq 'True' -and $member.DeleteAccounts -ne 'True') {

$lostPermissions += 'Add-only (no delete) not possible'

}

}

elseif ($member.RetrieveAccounts -eq 'True' -or $member.UseAccounts -eq 'True') {

$targetRole = 'View'

if ($member.UseAccounts -eq 'True' -and $member.RetrieveAccounts -ne 'True') {

$lostPermissions += 'Connect-only (no view password) not possible'

}

}

# Check for special permissions that need attention

if ($member.InitiateCPMAccountManagementOperations -eq 'True' -and $targetRole -eq 'View') {

$lostPermissions += 'CPM trigger permission needs custom handling'

}

$permissionReport += [PSCustomObject]@{

SafeName = $member.SafeName

MemberName = $member.MemberName

CurrentPermissions = ($member.PSObject.Properties | Where-Object { $_.Value -eq 'True' }).Name -join ','

TargetRole = $targetRole

LostPermissions = $lostPermissions -join '; '

RequiresReview = ($lostPermissions.Count -gt 0)

}

}

$permissionReport | Export-Csv "$extractPath\Permission_Translation.csv" -NoTypeInformation

$needsReview = ($permissionReport | Where-Object RequiresReview -eq $true).Count

Write-Host "$needsReview permission mappings require stakeholder review" -ForegroundColor Yellow

## 1.5 Phase 1 Deliverables & Gate

| Deliverable | Purpose | Gate Criteria |
| --- | --- | --- |
| Accounts.csv | All human accounts | Count matches CyberArk |
| NHI_Candidates.csv | Non-human identities | App owners identified for all |
| Integration_Dependencies.csv | All integrations | Cutover plan for each |
| Permission_Translation.csv | Permission mapping | Stakeholder sign-off obtained |
| Discovery_Report.txt | Summary statistics | Reviewed by project sponsor |

✅ GATE: Do not proceed to Phase 2 until all NHI app owners are identified and permission translation is approved.

PHASE 2: INFRASTRUCTURE SETUP & BENCHMARKING

Duration: 2-3 Weeks  |  Focus: SETUP + TEST

## 2.1 Secret Server Deployment (Standard)

Deploy Secret Server infrastructure as in v1.0.

## 2.2 NEW: Scalability Benchmarking

🔴 RISK: Delinea has been criticized for API performance under heavy load. Benchmark BEFORE migration.

# Create test secrets for benchmarking

$testFolder = New-TssFolder -TssSession $session -FolderName 'Benchmark_Test' -ParentFolderId 1

# Generate 1000 test secrets

$testSecrets = @()

for ($i = 1; $i -le 1000; $i++) {

$stub = Get-TssSecretStub -TssSession $session -SecretTemplateId 6001 -FolderId $testFolder.Id

$stub.Name = "Benchmark_Test_$i"

$stub.SetFieldValue('Machine', "test$i.domain.com")

$stub.SetFieldValue('Username', 'testuser')

$stub.SetFieldValue('Password', 'TestP@ss123')

$testSecrets += New-TssSecret -TssSession $session -SecretStub $stub

}

# Benchmark: API response times

$results = @()

foreach ($secret in $testSecrets) {

$start = Get-Date

$retrieved = Get-TssSecret -TssSession $session -Id $secret.Id

$elapsed = (Get-Date) - $start

$results += $elapsed.TotalMilliseconds

}

$avgLatency = ($results | Measure-Object -Average).Average

$maxLatency = ($results | Measure-Object -Maximum).Maximum

$p95Latency = ($results | Sort-Object)[[math]::Floor($results.Count * 0.95)]

Write-Host "API Benchmark Results:"

Write-Host "  Average latency: $([math]::Round($avgLatency, 2))ms"

Write-Host "  P95 latency:     $([math]::Round($p95Latency, 2))ms"

Write-Host "  Max latency:     $([math]::Round($maxLatency, 2))ms"

⚠️ THRESHOLD: P95 latency should be <500ms. If exceeded, scale infrastructure before migration.

## 2.3 NEW: Integration Preparation

Prepare Secret Server integrations BEFORE migration:

# Configure SIEM integration (dual logging during parallel)

# Admin > Configuration > General > Syslog/CEF

# Point to SAME syslog target as CyberArk

# Configure AD integration

# Admin > Directory Services > Add Domain

# Sync groups that will need Secret Server access

# Document Secret Server API endpoints for app teams

$apiEndpoints = @{

'OAuth Token' = 'POST /oauth2/token'

'Get Secret' = 'GET /api/v1/secrets/{id}'

'Get Secret Field' = 'GET /api/v1/secrets/{id}/fields/{slug}'

'Search Secrets' = 'GET /api/v1/secrets?filter.searchText={query}'

}

$apiEndpoints | ConvertTo-Json | Out-File "$transformPath\SecretServer_API_Reference.json"

## 2.4 NEW: Iris AI Configuration (If Available)

If Delinea Iris AI is included, configure for post-migration monitoring:

• Enable behavioral analytics for anomaly detection

• Configure alerting for unusual access patterns

• Set baseline during parallel period

• Flag any access from unknown applications

PHASE 3: ENHANCED DATA TRANSFORMATION

Duration: 2-3 Weeks  |  Focus: TRANSFORM

## 3.1 Account Classification

Classify accounts into migration waves based on risk:

| Wave | Account Type | Risk Level | Migration Order |
| --- | --- | --- | --- |
| Wave 1 | Test/Dev accounts | Low | First - validate process |
| Wave 2 | Standard user accounts | Medium | After Wave 1 validated |
| Wave 3 | Infrastructure accounts | Medium-High | With change window |
| Wave 4 | NHIs without integrations | High | Coordinated with app teams |
| Wave 5 | NHIs with CCP/AAM | Critical | Last - requires app cutover |

# Classify accounts into waves

$accounts = Import-Csv "$extractPath\Accounts.csv"

$nhis = Import-Csv "$extractPath\NHI_Candidates.csv"

$nhiIds = $nhis.AccountId

$classifiedAccounts = @()

foreach ($account in $accounts) {

$wave = 2  # Default: Standard

# Wave 1: Test/Dev

if ($account.safeName -match 'test|dev|sandbox|poc') {

$wave = 1

}

# Wave 3: Infrastructure

elseif ($account.platformId -match 'Cisco|Juniper|F5|VMware|ESXi') {

$wave = 3

}

# Wave 4/5: NHIs

elseif ($account.id -in $nhiIds) {

$nhi = $nhis | Where-Object { $_.AccountId -eq $account.id }

if ($nhi.AccessedBy -match 'CCP|AAM|AppUser') {

$wave = 5  # CCP/AAM integration

} else {

$wave = 4  # NHI without CCP

}

}

$classifiedAccounts += [PSCustomObject]@{

AccountId = $account.id

AccountName = $account.name

SafeName = $account.safeName

Platform = $account.platformId

Wave = $wave

IsNHI = ($account.id -in $nhiIds)

}

}

$classifiedAccounts | Export-Csv "$transformPath\Classified_Accounts.csv" -NoTypeInformation

# Summary by wave

$classifiedAccounts | Group-Object Wave | Format-Table Name, Count

## 3.2 Enhanced Permission Transform

Apply approved permission translation with audit trail:

# Load approved translation matrix

$approvedTranslation = Import-Csv "$extractPath\Permission_Translation_APPROVED.csv"

# Generate Secret Server permission assignments

$ssPermissions = @()

foreach ($perm in $approvedTranslation) {

$ssPermissions += [PSCustomObject]@{

FolderId = $folderMapping[$perm.SafeName]

MemberName = $perm.MemberName

Role = $perm.TargetRole

OriginalCyberArkPerms = $perm.CurrentPermissions

ApprovedBy = $perm.ApprovedBy

ApprovalDate = $perm.ApprovalDate

}

}

$ssPermissions | Export-Csv "$transformPath\SS_Permissions.csv" -NoTypeInformation

PHASE 4: WAVE-BASED MIGRATION EXECUTION

Duration: 4-6 Weeks  |  Focus: LOAD

## 4.1 Wave Execution Framework

Execute migration in waves with validation gates between each:

| Wave | Duration | Gate Criteria to Proceed |
| --- | --- | --- |
| Wave 1 (Test/Dev) | 1 week | >95% heartbeat success, no critical issues |
| Wave 2 (Standard) | 1-2 weeks | >95% heartbeat, UAT sign-off |
| Wave 3 (Infrastructure) | 1 week | >95% heartbeat, network team sign-off |
| Wave 4 (NHI non-CCP) | 1 week | >95% heartbeat, app teams notified |
| Wave 5 (NHI CCP/AAM) | 1-2 weeks | App cutover complete, >95% success |

# Wave execution function

function Execute-MigrationWave {

param($WaveNumber)

$waveAccounts = Import-Csv "$transformPath\Classified_Accounts.csv" |

Where-Object { $_.Wave -eq $WaveNumber }

Write-Host "=== EXECUTING WAVE $WaveNumber ==="

Write-Host "Accounts in wave: $($waveAccounts.Count)"

$results = @()

foreach ($account in $waveAccounts) {

# Extract password from CyberArk

$pw = Get-PASAccountPassword -AccountID $account.AccountId -Reason 'Migration Wave $WaveNumber'

# Create in Secret Server

$stub = Get-TssSecretStub -TssSession $session -SecretTemplateId $templateMapping[$account.Platform] -FolderId $folderMapping[$account.SafeName]

$stub.Name = $account.AccountName

# ... set fields ...

try {

$newSecret = New-TssSecret -TssSession $session -SecretStub $stub

$results += [PSCustomObject]@{ AccountId = $account.AccountId; Status = 'Success'; SecretId = $newSecret.Id }

} catch {

$results += [PSCustomObject]@{ AccountId = $account.AccountId; Status = 'Failed'; Error = $_.Exception.Message }

}

}

# Wave validation

$success = ($results | Where-Object Status -eq 'Success').Count

$failed = ($results | Where-Object Status -eq 'Failed').Count

$successRate = [math]::Round(($success / $results.Count) * 100, 2)

Write-Host "Wave $WaveNumber Results: $successRate% success ($success/$($results.Count))"

# Gate check

if ($successRate -lt 95) {

Write-Host 'GATE FAILED: Success rate below 95%. Investigate before proceeding.' -ForegroundColor Red

return $false

}

return $true

}

## 4.2 NEW: CCP/AAM Application Cutover (Wave 5)

🔴 RISK: This is the highest-risk phase. Applications using CyberArk CCP/AAM must be updated to use Secret Server API.

For each CCP/AAM application:

• 1. Coordinate maintenance window with app team

• 2. Migrate associated credentials to Secret Server

• 3. Update application code to use Secret Server SDK/API

• 4. Test credential retrieval in non-prod

• 5. Deploy to production during window

• 6. Validate application functionality

• 7. Rollback plan: revert code, credentials still in CyberArk

# CCP to Secret Server API mapping

$apiMapping = @{

'CyberArk CCP GetPassword' = 'Secret Server GET /api/v1/secrets/{id}/fields/password'

'CyberArk AAM CP SDK' = 'Secret Server .NET SDK or REST API'

'CyberArk Conjur' = 'Secret Server REST API (different architecture)'

}

⚠️ CRITICAL: Maintain CyberArk CCP availability until ALL applications are cutover and validated.

PHASE 5: EXTENDED PARALLEL RUNNING

Duration: 4-6 Weeks  |  Focus: VALIDATE + MONITOR

## 5.1 Dual-System Operation

Both systems run simultaneously. This period is EXTENDED from v1.0 (was 2-4 weeks) to allow thorough validation.

| System | Status | Access |
| --- | --- | --- |
| CyberArk | Active (read-only for users) | Admin access for rollback |
| Secret Server | Active (primary) | Full user access |
| SIEM | Receiving from BOTH | Dual logging |

## 5.2 NEW: Comprehensive Validation

# Daily validation during parallel period

$date = Get-Date -Format 'yyyy-MM-dd'

# 1. Count validation

$cyberArkCount = (Get-PASAccount).Count

$ssCount = (Search-TssSecret -TssSession $session).Count

$countMatch = $cyberArkCount -eq $ssCount

# 2. Heartbeat validation

$allSecrets = Search-TssSecret -TssSession $session

$failedHB = ($allSecrets | Where-Object LastHeartBeatStatus -eq 'Failed').Count

$hbSuccessRate = [math]::Round((($allSecrets.Count - $failedHB) / $allSecrets.Count) * 100, 2)

# 3. NHI validation - check applications still working

$nhiSecrets = $allSecrets | Where-Object { $_.SecretName -in $nhiCandidates.AccountName }

$nhiAccessed = ($nhiSecrets | Where-Object { $_.LastAccessed -gt (Get-Date).AddDays(-1) }).Count

# 4. SIEM validation - events flowing

# (Manual check or SIEM API query)

# 5. Permission validation - spot check

$permissionIssues = @()  # Populated from UAT feedback

$validationReport = @"

PARALLEL VALIDATION REPORT - $date

====================================

Count Match:        $countMatch (CyberArk: $cyberArkCount, SS: $ssCount)

Heartbeat Success:  $hbSuccessRate%

NHIs Accessed (24h): $nhiAccessed / $($nhiSecrets.Count)

Permission Issues:  $($permissionIssues.Count)

"@

Write-Host $validationReport

## 5.3 Rollback Triggers

Rollback to CyberArk if ANY of these thresholds are breached:

| Metric | Threshold | Action |
| --- | --- | --- |
| Heartbeat success rate | <90% | STOP - Investigate immediately |
| NHI access failures | >5% | STOP - Check application health |
| Permission escalations | Any unauthorized | STOP - Security review |
| SIEM event gap | >1 hour | WARNING - Check integration |
| User-reported issues | >10/day | REVIEW - May need rollback |

PHASE 6: FINAL CUTOVER & DECOMMISSION

Duration: 2-3 Weeks  |  Focus: CUTOVER

## 6.1 Pre-Cutover Checklist

| Requirement | Status | Sign-off Required |
| --- | --- | --- |
| All waves completed successfully | ☐ | Project Manager |
| Heartbeat >95% for 2 consecutive weeks | ☐ | PAM Engineer |
| All NHI applications cutover | ☐ | App Owners |
| All integrations functional | ☐ | Integration Owners |
| No rollback triggers in 2 weeks | ☐ | PAM Engineer |
| UAT sign-off from key users | ☐ | Business Stakeholders |
| Compliance audit passed | ☐ | Compliance Team |
| Runbooks complete | ☐ | NOC Manager |

## 6.2 Archive CyberArk Data

# Archive BEFORE decommission

# 1. PSM Recordings

$recordings = Get-PASPSMRecording -Limit 10000

foreach ($rec in $recordings) {

Export-PASPSMRecording -RecordingID $rec.RecordingID -Path "$archivePath\Recordings\"

}

# 2. Audit Logs (EVD utility on CyberArk server)

# EVD.exe /LogNumOfDays=730 /OutputPath=C:\AuditArchive

# 3. Safe configurations

$safes | ConvertTo-Json -Depth 10 | Out-File "$archivePath\SafeConfigs.json"

# 4. Platform configurations

foreach ($platform in $platforms) {

Export-PASPlatform -PlatformID $platform.PlatformID -Path "$archivePath\Platforms\"

}

## 6.3 Compliance Validation

# Generate compliance comparison report

$complianceReport = @"

COMPLIANCE VALIDATION REPORT

============================

ACCOUNT COVERAGE

CyberArk accounts:     $cyberArkCount

Secret Server secrets: $ssCount

Variance:              $([math]::Abs($cyberArkCount - $ssCount))

AUDIT TRAIL

CyberArk logs archived: $(Test-Path "$archivePath\AuditLogs")

Secret Server logging:  Active

SIEM integration:       Active

ACCESS CONTROL

Permission mappings:    Approved on [DATE]

Approved by:            [STAKEHOLDER]

"@

$complianceReport | Out-File "$archivePath\ComplianceValidation.txt"

# Appendix A: NHI Migration Procedures

## A.1 Service Account Migration

• Identify all Windows services using the account

• Coordinate maintenance window with service owners

• Update service credentials after Secret Server migration

• Validate service startup

## A.2 Scheduled Task Account Migration

• List all scheduled tasks using the account

• Update task credentials post-migration

• Verify task execution

## A.3 Application Credential (CCP/AAM) Migration

| Step | Action | Owner |
| --- | --- | --- |
| 1 | Migrate credential to Secret Server | PAM Engineer |
| 2 | Update application code to SS API | App Developer |
| 3 | Test in non-production | App Team |
| 4 | Deploy during maintenance window | App Team |
| 5 | Validate credential retrieval | PAM Engineer |
| 6 | Monitor for 48 hours | NOC |

## A.4 API Key Migration

• Document all systems using the API key

• Generate new key in Secret Server if needed

• Update all consuming systems

• Revoke old key after validation

# Appendix B: Integration Cutover Procedures

## B.1 SIEM Integration

# CyberArk syslog -> Keep active during parallel

# Secret Server syslog -> Configure to SAME target

# After cutover -> Disable CyberArk syslog

## B.2 ServiceNow Integration

• Update ServiceNow credential resolver to Secret Server

• Test discovery and automation workflows

• Update runbooks with new procedures

## B.3 SOAR Integration

• Update playbooks to use Secret Server API

• Test credential retrieval in playbooks

• Validate automated response workflows

# Appendix C: Enhanced Command Reference

## C.1 NHI Discovery Commands

Get-PASAccountActivity -AccountID <id>  # Check access patterns

Get-PASComponentDetail -Component CCP   # List CCP applications

## C.2 Wave Migration Commands

# Filter accounts by wave

$wave1 = Import-Csv Classified_Accounts.csv | Where-Object Wave -eq 1

# Execute wave with validation

Execute-MigrationWave -WaveNumber 1

## C.3 Validation Commands

# Bulk heartbeat

Search-TssSecret -TssSession $session | ForEach-Object { Start-TssSecretHeartbeat -TssSession $session -Id $_.SecretId }

# Check heartbeat status

Search-TssSecret -TssSession $session | Where-Object LastHeartBeatStatus -eq 'Failed'