CyberArk On-Premises to Cloud

Migration Plan

Enterprise Privileged Access Management | Cloud Transformation

Document Date: March 2, 2026  |  Classification: Confidential

# 1. Executive Summary

This document provides a comprehensive migration plan for transitioning CyberArk Privileged Access Management (PAM) from on-premises infrastructure to CyberArk Privilege Cloud (SaaS). The migration aims to reduce infrastructure overhead, improve scalability, and leverage cloud-native capabilities while maintaining zero-disruption to privileged access operations.

| Migration Type | Target Platform | Est. Timeline | Risk Level |
| --- | --- | --- | --- |
| On-Prem to SaaS | CyberArk Privilege Cloud | 16-24 Weeks | Medium-High |

## Migration Objectives

- Eliminate on-premises Vault, PVWA, CPM, and PSM infrastructure

- Migrate all safes, accounts, platforms, and connectors to Privilege Cloud

- Preserve existing integrations: Active Directory, SIEM, ITSM, and application integrations

- Maintain compliance posture (HIPAA, PCI-DSS, SOX) throughout migration

- Achieve feature parity or enhancement post-migration

# 2. Scope & Inventory

## 2.1 Components Being Migrated

| Component | On-Prem | Cloud Equivalent |
| --- | --- | --- |
| Vault | CyberArk Digital Vault (self-hosted) | Privilege Cloud Vault (Managed by Cyberark) |
| PVWA | Web UI on IIS (self-hosted) | Privilege Cloud Portal (SaaS) |
| CPM | Central Policy Manager (on-prem) | Connector (on-prem agent, cloud-managed) |
| PSM | Privileged Session Manager (on-prem) | PSM Connector (on-prem agent, cloud-managed) |
| PSMP | PSM for SSH (on-prem) | PSMP Connector (on-prem agent, cloud-managed) |
| PTA | Privileged Threat Analytics (optional) | Privilege Cloud Analytics (SaaS) |
| AIM/CCP | App Identity Manager / CCP | Secrets Manager Credential Providers |

## 2.2 Pre-Migration Discovery Checklist

- Document all Safes, permissions, and Safe member assignments

- Catalog all Platforms (built-in and custom)

- Enumerate all CPM Plugins (built-in, custom, out-of-box)

- Document all PSM Connection Components and Connection Manager configurations

- Map all LDAP/AD directory integrations and group synchronizations

- Identify all API integrations (CCP, REST API consumers, LDAP integration)

- Inventory PSM session recordings and audit log retention requirements

- Document all dual-control workflows and ticketing system integrations

- Identify accounts with custom password change processes or exception lists

# 3. Cloud Architecture Overview

## 3.1 Privilege Cloud Architecture

CyberArk Privilege Cloud uses a hybrid model: the Vault and PVWA portal are fully managed by CyberArk in their cloud, while CPM, PSM, and PSMP Connectors remain on-premises as lightweight agents. This allows the cloud Vault to manage privileged accounts without requiring direct inbound network access into your on-prem environment.

| Layer | Description |
| --- | --- |
| Cloud (CyberArk-Managed) | Vault, PVWA Portal, PTA Analytics, Identity Security Platform, Auditing & Reporting |
| On-Premises (Customer-Managed) | CPM Connector, PSM Connector, PSMP Connector, Secure Tunnel |
| Customer Network | AD/LDAP, Target systems, SIEM, ITSM, App servers with CCP agents |
| Connectivity | Secure Tunnel over TLS 1.2/1.3 to CyberArk cloud (TCP 443 outbound only) |

## 3.2 Network Requirements

- All connector traffic is outbound-only over TCP 443 — no inbound firewall rules required

- Secure Tunnel (CyberArk Connector Management) replaces VPN-based vault access

- DNS resolution for *.privilegecloud.cyberark.com and *.cyberark.cloud required

- CPM/PSM servers need internal network access to target systems (unchanged from on-prem)

- Connector servers: minimum 4 vCPU / 8 GB RAM, Windows Server 2019/2022

# 4. Migration Approach & Phasing

## 4.1 Migration Strategy: Parallel-Run

The recommended approach is a parallel-run strategy where both the on-premises environment and Privilege Cloud are operational simultaneously. Accounts are migrated in batches by Safe/business unit, with validation performed before each batch is cut over. The on-premises Vault is not decommissioned until 100% of accounts have been validated in the cloud.

## 4.2 Phase Overview

| Phase | Name | Key Activities | Duration |
| --- | --- | --- | --- |
| 1 | Discovery & Planning | Inventory, dependency mapping, gap analysis, team training | 2-3 Weeks |
| 2 | Privilege Cloud Setup | Tenant provisioning, connector install, AD sync, SIEM/ITSM integration | 3-4 Weeks |
| 3 | Platform Migration | Export/import all platforms, validate CPM plugins, test password rotation | 2-3 Weeks |
| 4 | Pilot Migration | Migrate IT team Safes, validate end-to-end workflows, refine runbooks | 2-3 Weeks |
| 5 | Production Migration | Batch migration by Safe group, validate each batch, update integrations | 5-8 Weeks |
| 6 | Cutover & Validation | Final sync, DNS/URL cutover, parallel operation period | 2-3 Weeks |
| 7 | Decommission | On-prem Vault shutdown, audit log archival, infrastructure teardown | 2-4 Weeks |

# 5. Detailed Phase Execution

## Phase 1: Discovery & Planning

- Export full Safe list with permissions: GET /PasswordVault/API/Safes

- Export all accounts metadata via REST API or PACLI FINDFILES command

- Document all CPM plugins in use — identify which are natively supported in Privilege Cloud vs. custom

- Document PSM Connection Components and confirm cloud compatibility

- Map all Active Directory groups used for LDAP sync

- Inventory all CCP/AIM integrations and consuming applications

- Conduct Privilege Cloud feature parity assessment against current on-prem capabilities

- Engage CyberArk PS team or partner for tenant provisioning and licensing confirmation

## Phase 2: Privilege Cloud Environment Setup

- Provision Privilege Cloud tenant (coordinate with CyberArk account team)

- Install Connector Management Agent on dedicated Windows servers

- Configure Secure Tunnel — verify outbound TCP 443 connectivity to CyberArk cloud

- Install and register CPM Connector, PSM Connector, PSMP Connector

- Configure LDAP/Active Directory integration in Privilege Cloud portal

- Set up user provisioning — SAML SSO via Entra ID / ADFS or Privilege Cloud Identity

- Configure SIEM integration (Syslog forwarding or direct API — Splunk, Graylog, etc.)

- Configure ITSM dual-control integration (ServiceNow, Jira) via REST API

- Validate admin access, Safe creation, and basic account onboarding end-to-end

## Phase 3: Platform Migration

Platforms define password policy, connection method, and reconciliation behavior. All platforms must be migrated before accounts.

- Export built-in platforms from on-prem PVWA (Admin > Platform Management > Export as ZIP)

- Import platforms into Privilege Cloud portal

- Re-create custom CPM plugins — validate against Privilege Cloud Connector compatibility matrix

- Test password rotation for each platform type in a sandbox environment

- Validate PSM Connection Components for RDP, SSH, Web, database connection types

- Document any platforms requiring custom development or CyberArk support tickets

## Phase 4: Pilot Migration

Migrate IT/Security team Safes first — users who can validate functionality and troubleshoot issues.

- Freeze pilot Safes — no password changes during export window

- Export pilot accounts via REST API or PACLI

- Transform data: map Safe names, platform names, and permission sets to Privilege Cloud equivalents

- Import accounts using Password Upload Utility (PUU) or REST API bulk import

- Run Heartbeat checks on all imported accounts to validate credential accuracy

- Test session recordings via PSM — validate recording storage configuration

- Test dual-control workflows and verify ITSM ticket integration

- Validate CCP/AIM application credential retrieval for pilot applications

- Document issues, update runbooks, obtain stakeholder sign-off

## Phase 5: Production Migration

Migrate remaining Safes in batches by department, system type, or business unit. Recommended batch order: infrastructure/network, server/OS, database, application, cloud workloads.

- Establish a freeze window for each Safe batch before export (minimum 2-hour freeze)

- Export batch accounts — validate record count against on-prem inventory

- Import and run Heartbeat validation — target >98% success rate before proceeding

- Notify application owners and update any hardcoded CCP endpoint references

- Maintain both environments active until batch is fully validated

- Escalation path: re-export and re-import failed accounts; do not manually reset passwords

## Phase 6: Cutover & Validation

- Migrate final batch of Safes and run full Heartbeat sweep

- Update all DNS/URL references from on-prem PVWA URL to Privilege Cloud portal URL

- Update CCP/AIM application configurations to point to Privilege Cloud Credential Provider

- Run parallel operations for minimum 2 weeks — both environments accessible

- Conduct User Acceptance Testing with all business unit representatives

- Validate session recordings, audit logs, and report generation

- Obtain sign-off from CISO, Compliance, and Application owners

## Phase 7: Decommission

- Export all audit logs from on-prem Vault using EVD utility (retain per compliance requirements)

- Archive PSM session recordings from Recording Safes or external SMB storage

- Revoke on-prem Vault admin accounts and CCP application credentials

- Shut down PVWA, CPM, PSM, PSMP on-premises servers

- Perform final backup of Vault database before shutdown

- Decommission Vault servers and update CMDB, asset management systems

- Update disaster recovery documentation to reflect Privilege Cloud RPO/RTO (CyberArk SLA)

# 6. Key Integration Updates

| Integration | On-Prem Configuration | Privilege Cloud Configuration |
| --- | --- | --- |
| Active Directory | LDAP bind to on-prem PVWA | LDAP Connector via Privilege Cloud portal |
| SSO / MFA | RADIUS, SAML via on-prem IdP | Native SAML/OIDC integration with Entra ID / Okta |
| SIEM (Splunk/Graylog) | Syslog from on-prem Vault | Syslog from Connector or Privilege Cloud native integration |
| ServiceNow / Jira | REST API dual-control plugin | REST API dual-control (same API, new base URL) |
| CCP / AIM Apps | CCP installed on-prem, apps query local CCP | Credential Provider installed on-prem, queries cloud Vault |
| Ansible / Terraform | CyberArk Ansible Collection (on-prem API) | Same collection, updated PVWA URL to Privilege Cloud |
| Splunk Add-on | CyberArk Add-on for Splunk | Updated to Privilege Cloud syslog format |

# 7. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| PSM session recordings not transferable to cloud | High | Medium | Archive to secure on-prem storage; keep read-only on-prem access for audit |
| Custom CPM plugins not compatible with Privilege Cloud Connector | Medium | High | Audit all plugins pre-migration; rebuild or use CyberArk Marketplace alternatives |
| Application CCP integrations break during cutover | Medium | High | Parallel-run both CCP environments; update app configs in batches with rollback plan |
| Latency increase for PSM sessions via cloud routing | Low | Medium | PSM Connectors remain on-prem; session traffic stays local — only management plane is cloud |
| Secure Tunnel connectivity issues in restricted network environments | Low | High | Pre-test TCP 443 outbound to *.cyberark.cloud; coordinate with network/firewall team |
| Compliance gaps during parallel-run period | Medium | High | Maintain audit logging on both systems; document transition period for auditors |
| License overages during parallel-run period | Low | Low | Negotiate temp dual-licensing with CyberArk account team before migration start |

# 8. Rollback Plan

The parallel-run strategy inherently provides a rollback path. The on-premises environment remains fully operational throughout the migration.

Rollback Triggers

- Heartbeat failure rate exceeds 5% on any migration batch

- Critical application integration failure that cannot be resolved within 4-hour SLA

- Compliance or audit finding that invalidates the cloud environment

- Privilege Cloud SLA breach during migration window

Rollback Steps

- Halt all ongoing migrations immediately

- Re-route all PVWA user traffic back to on-premises PVWA URL

- Revert CCP application configurations to on-prem Credential Provider endpoints

- Assess root cause — engage CyberArk support if platform-related

- Document failures, update runbooks, and re-schedule migration after resolution

# 9. Success Criteria & KPIs

| Success Metric | Target |
| --- | --- |
| Account Heartbeat Pass Rate Post-Migration | >= 99% |
| PSM Session Launch Success Rate | >= 99.5% |
| CCP Credential Retrieval Availability | 99.9% (aligned to Privilege Cloud SLA) |
| Zero Privilege Escalation Incidents During Migration | 0 incidents |
| Compliance Audit Log Continuity | No gaps in audit trail |
| On-Prem Infrastructure Decommission | 100% within 60 days of final batch cutover |
| User Satisfaction (post-migration survey) | >= 90% positive response |

# 10. Team Roles & Responsibilities

| Role | Responsibilities | Owner |
| --- | --- | --- |
| Migration Lead / Security Engineer | Overall migration coordination, technical execution, runbook ownership | TBD |
| CyberArk Administrator | Safe/account export-import, platform migration, Heartbeat validation | TBD |
| Network / Infrastructure Engineer | Connector server provisioning, firewall rules, Secure Tunnel setup | TBD |
| Identity / IAM Engineer | AD integration, SAML SSO configuration, Entra ID setup | TBD |
| Application Owners | CCP integration validation, UAT sign-off | Per Team |
| Security Compliance | Audit log continuity review, compliance sign-off | TBD |
| CyberArk Professional Services | Tenant provisioning support, technical escalation | CyberArk PS |

CONFIDENTIAL — FOR INTERNAL USE ONLY