iOPEX  |  SHIFT Migration System  |  CyberArk → KeeperPAM

Runbook P6 — Parallel Running & Cutover

CyberArk → KeeperPAM Migration | SHIFT System

| Phase | P6 — Parallel Running & Cutover |
| --- | --- |
| Duration | 4–6 weeks |
| Agents | 15 → 05 → 06 → 07 |
| Gate | YC-P6 — 100% fleet migrated, CISO + client exec sign-off |
| Classification | CONFIDENTIAL |

────────────────────────────────────────────────────────────────────────────────

Scope: Both CyberArk on-prem and KeeperPAM run simultaneously. Fleet management tracks per-account migration status. Final cutover when all accounts verified in KeeperPAM.

Duration: 4–6 weeks

Prerequisite: P5 complete, all waves migrated, all integrations repointed.

Who runs this: iOPEX delivery engineer + client operations team

Agent sequence: `15-hybrid-fleet` → `05-heartbeat` → `06-integration` → `07-compliance`

────────────────────────────────────────────────────────────────────────────────

P6 Checklist

☐  All 5 waves migrated (P5 complete)

☐  All application integrations repointed to KeeperPAM

☐  Hybrid fleet map initialized

☐  Weekly heartbeat schedule agreed with client

☐  Cutover criteria defined and documented

☐  Rollback plan documented (point-in-time: can revert to CyberArk)

────────────────────────────────────────────────────────────────────────────────

Parallel Running Concept

During P6, both systems operate simultaneously:

CyberArk on-prem:** Still active. CPM rotation may be running (configurable).

KeeperPAM:** Primary for all migrated accounts. Rotation engine active.

Agent 15:** Tracks every account's state, routes credential retrieval, detects split-brain scenarios.

The parallel period exists to:

Confirm all integrations are using KeeperPAM (not CyberArk)

Catch any accounts missed during P5 migration

Build operational confidence in KeeperPAM before CyberArk is decommissioned

Provide a safety net for rapid rollback

────────────────────────────────────────────────────────────────────────────────

Agent 15 — Hybrid Fleet Manager

Initialize the fleet map from P5 ETL results. Tracks every account's migration status.

# P5 run: Initialize fleet map

az containerapp exec \

--name "$APP_NAME" --resource-group "$RG" \

--command "python3 cli.py agent 15-hybrid-fleet --phase P5"

# P6 run: Verify target retrieval and detect stuck accounts (run weekly)

az containerapp exec \

--name "$APP_NAME" --resource-group "$RG" \

--command "python3 cli.py agent 15-hybrid-fleet --phase P6"

Migration Status Lifecycle per Account:

| Status | Meaning | Action |
| --- | --- | --- |
| on_prem | Only in CyberArk | Migrate (should not exist after Wave 5) |
| migrating | ETL in progress | Monitor |
| parallel | In both systems | Verify KeeperPAM version, remove from CyberArk |
| cloud_primary | KeeperPAM primary, CyberArk fallback | Verify apps using KeeperPAM, prepare decommission |
| migrated | KeeperPAM only | Complete |
| stuck | No rotation for 48h+ | Investigate — escalate |

View fleet status:

az containerapp exec \

--name "$APP_NAME" --resource-group "$RG" \

--command "cat output/reports/agent_15_hybrid_fleet_P6.json | python3 -c \"

import json, sys

data = json.load(sys.stdin)

by_status = data.get('by_status', {})

print('Fleet Status Summary:')

for status, count in by_status.items():

print(f'  {status:20s}: {count}')

stuck = data.get('stuck_accounts', [])

if stuck:

print(f'STUCK ACCOUNTS ({len(stuck)}):')

for a in stuck[:10]:

print(f'  {a[\\\"account_name\\\"]} (last rotation: {a[\\\"last_rotation_attempt\\\"]})')

\""

Stuck account resolution:

A stuck account is one with no successful rotation in 48+ hours. Causes:

| Cause | Fix |
| --- | --- |
| Network path blocked | Open firewall from KeeperPAM rotation engine to target host |
| Credential mismatch | Manually reset password in KeeperPAM, trigger rotation |
| Record type mismatch | Re-map to correct record type |
| Host unreachable | Verify host is online; update record with new address |
| Rotation policy not set | Configure rotation policy in KeeperPAM admin |

────────────────────────────────────────────────────────────────────────────────

Agent 05 — Heartbeat Validation (P6 Weekly)

Run weekly throughout the parallel period to track ongoing health.

az containerapp exec \

--name "$APP_NAME" --resource-group "$RG" \

--command "python3 cli.py agent 05-heartbeat --phase P6"

Track heartbeat trend weekly:

| Week | Target Pass Rate | Gate Action |
| --- | --- | --- |
| Week 1 | ≥ 95% | Continue parallel running |
| Week 2 | ≥ 97% | Address any remaining stuck accounts |
| Week 3 | ≥ 99% | Begin cutover preparation |
| Week 4+ | 100% | Ready for cutover |

────────────────────────────────────────────────────────────────────────────────

Agent 06 — Integration Verification (P6)

Re-scan codebases to confirm ALL CyberArk integration patterns are gone.

az containerapp exec \

--name "$APP_NAME" --resource-group "$RG" \

--command "python3 cli.py agent 06-integration --phase P6"

P6 pass condition: 0 CyberArk integration patterns detected across all scanned directories.

If patterns remain:

Identify which app team has not completed repointing

Escalate with the specific file and line number from the scan report

Do not cutover until 0 patterns remain

────────────────────────────────────────────────────────────────────────────────

Agent 07 — Compliance (P6 — Ongoing Evidence)

az containerapp exec \

--name "$APP_NAME" --resource-group "$RG" \

--command "python3 cli.py agent 07-compliance --phase P6"

P6 compliance focuses on:

Dual-system access logging continuity

Segregation of duties during parallel running

Evidence that CyberArk access is restricted (not expanded) during parallel period

SOX: evidence that privileged access controls are maintained throughout transition

────────────────────────────────────────────────────────────────────────────────

Cutover Decision

Cutover is the point at which CyberArk on-prem is frozen (read-only) and KeeperPAM becomes the sole authoritative PAM system.

Cutover criteria (all must be met):

| Criterion | Target | Source |
| --- | --- | --- |
| Fleet migrated status | 100% of accounts | Agent 15 fleet report |
| Heartbeat pass rate | 100% | Agent 05 report |
| Integration repointing | 0 CyberArk patterns | Agent 06 scan |
| Stuck accounts | 0 | Agent 15 report |
| Compliance gaps | 0 HIGH/CRITICAL | Agent 07 report |
| App team confirmations | 100% of impacted teams | Signed-off tickets |

When criteria are met, schedule the cutover window:

# Final heartbeat before cutover

az containerapp exec \

--name "$APP_NAME" --resource-group "$RG" \

--command "python3 cli.py agent 05-heartbeat --phase P6"

# Final fleet check

az containerapp exec \

--name "$APP_NAME" --resource-group "$RG" \

--command "python3 cli.py agent 15-hybrid-fleet --phase P6"

# Final integration scan

az containerapp exec \

--name "$APP_NAME" --resource-group "$RG" \

--command "python3 cli.py agent 06-integration --phase P6"

All pass → proceed with cutover.

Cutover execution:

Notify all stakeholders — maintenance window start

Freeze CyberArk: disable CPM on ALL remaining accounts

Set CyberArk to read-only mode (or revoke write permissions from migration service account)

Update DNS / load balancer aliases from PVWA to KeeperPAM where applicable

Confirm all app teams verify their credentials are being retrieved from KeeperPAM

Run final Agent 05 heartbeat — must be 100%

Declare cutover complete

# Post-cutover final heartbeat

az containerapp exec \

--name "$APP_NAME" --resource-group "$RG" \

--command "python3 cli.py agent 05-heartbeat --phase P6"

────────────────────────────────────────────────────────────────────────────────

P6 Output Files

| File | Contents |
| --- | --- |
| output/reports/agent_15_hybrid_fleet_P5.json | Initial fleet map |
| output/reports/agent_15_hybrid_fleet_P6.json | Weekly fleet status |
| output/reports/agent_05_heartbeat_P6.json | Weekly heartbeat |
| output/reports/agent_06_integration_P6.json | Integration re-scan results |
| output/reports/agent_07_compliance_P6.json | Parallel running compliance evidence |

────────────────────────────────────────────────────────────────────────────────

P6 Troubleshooting

| Issue | Cause | Fix |
| --- | --- | --- |
| Split-brain: both CPM rotate same account | Hybrid mode not set to exclusive | Set HYBRID_MODE=exclusive in agent_config.json |
| Stuck accounts increasing week-over-week | Systemic rotation failure | Network / firewall audit required |
| App team reports wrong password | Old credentials cached | Force rotation in KeeperPAM; app team flushes cache |
| Integration scan still finding patterns | App deployed with old code | App team re-deployment required |
| CyberArk PVWA showing access attempts post-cutover | App still using CyberArk | Agent 06 re-scan to identify source |

────────────────────────────────────────────────────────────────────────────────

Yellow Checkpoint YC-P6

Gate before advancing to P7 (decommission). Requires:

☐  100% of accounts at `migrated` status in fleet report

☐  100% heartbeat pass rate

☐  0 CyberArk integration patterns in final scan

☐  0 stuck accounts

☐  Cutover completed and confirmed by all app teams

☐  CISO / security lead sign-off

☐  Client executive sign-off

☐  Change management ticket closed

# Advance to P7

az containerapp exec \

--name "$APP_NAME" --resource-group "$RG" \

--command "python3 cli.py advance"

────────────────────────────────────────────────────────────────────────────────

Next Step

→ [P7_decommission.md](P7_decommission.md) — CyberArk on-prem decommission, final audit report, project close-out.